## Plan
Client Company Name/DataSpan RFID-Based WIP Project Plan - Working Draft (EXAMPLE)
Project #
As of Date:
Team Contact Information
Client Project Contact (CPC): Name, Mobile #, Email address
Dataspan Sales Contact: DataSpan Sales Person, Mobile #, Email address
RFID Project Manager Contact: Jim Ferguson, DataSpan, 972-207-8317; jferguson@dataspan.com
Technical Project Contact: Name. Mobile #, Email address
Software PartnerContact (SPC): Contact Name, Company, Mobile #, Email Address
|  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19
Track | Activity | Owner
|  |  | 2019-08-12 | 2019-08-19 | 2021-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16
Business
Receive XYZ HW/SW/Tag Purchase Orders | bar: Wk 1
Issue DataSpan Hardware, SW, Tag, POs | bar: Wk 1 to Wk 2
Handheld Scanners Delivered | bar: Wk 1 to Wk 2; Wk 7
RFID Tags/Labels Delivered | bar: Wk 1 to Wk 2; Wk 7
Ship handheld scanner to DS | bar: Wk 1 to Wk 2; Wk 8
Pre-Installation Preparation
Administrative
Agree on Project Team Members | bar: Wk 1 to Wk 2
Set up weekly update conf call day/time | bar: Wk 1 to Wk 2
Review Component Delivery Schedule
Establish projected initial on-site date(s) | bar: Wk 1 to Wk 4
Set up tech team travel, hotel | bar: Wk 5
Confirm XYZ Vacation Schedules | bar: Wk 10
Confirm Partner & DS Vacation Schedules | bar: Wk 10
|  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk12 | Wk 13 | Wk14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19
|  |  | 2019-08-12 | 2019-08-19 | 2021-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16
Technical
Provide Final Software Requirements/Scope | bar: Wk 1 to Wk 2
Provide all asset types | bar: Wk 1 to Wk 2
Database fields approved
Develop and provide Integration Questionnaire | bar: Wk 1 to Wk 2
Request Relevant Integration Docs | bar: Wk 1 to Wk 2
New IT asset database fields populated | bar: Wk 5
Develop and remotely test HH & Portal software | bar: Wk 7
Ship Handheld to DS for testing | bar: Wk 5
Install and test scanner software | bar: Wk 6
Demo handheld/server on-line | bar: Wk 7
Procure and install on-site PC/WS | bar: Wk 9
Client database server set-up & available | bar: Wk 8
Client SQL Instance set-up/tested | bar: Wk 9
Load and test server software on-line | bar: Wk 8
Remotely demo the prototype to Client for comment | bar: Wk 11
On-Site Installation
|  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk12 | Wk 13 | Wk14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19
|  | Owner | 2019-08-12 | 2019-08-19 | 2021-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16
Client On-site Installation
| Team Meeting - site assessment, introductions, etc | On-site Team | bar: Wk14
| On-site building walk-through | On-site Team | bar: Wk14
| Technical Review Meeting | On-site Team | bar: Wk14
| Software Installation/Testing | On-site Team | bar: Wk14
| IT Asset Enrollment Training | On-site Team | bar: Wk14
| Handheld/Software Training | On-site Team | bar: Wk14
| Server Application Training | On-site Team | bar: Wk14
| Application Testing and Modifications | On-site Team | bar: Wk14
| Add'l modifications documented and scheduled | On-site Team | bar: Wk14
Post On-site Installation
| Add'l modifications completed and accepted | TBD | bar: Wk 15
Project accepted and signed off | bar: Wk 15
Legend
Forecasted Dates
Activity Begun
Activity Completed
New Activity

## Issues
|  |  | Raised | Date | Date |  |  | Due
# | Issue/Item | Severity | By | Recorded | Closed | Action Item | Owner | Date